## Master Activity Registry
Labour Mobility Navigator (MASAR) — Master Activity & Responsibility Registry
Project window 2026-06-01 to 2026-10-31 ¦ Yellow "Team Update" column: pick "Done" from the dropdown once an activity is actually finished
No. | Original WP | Activity | Description / Indicator | Responsible (Role) | Responsible (Name) | Status | Start Date | End Date | Source | Team Update
1 | WP1 Project Planning & Governance | Build Project Implementation Plan | Project implementation plan approved ¦ Target: 1 Approved Plan ¦ Verification: Approved Project Plan | LM Navigator Implementation Lead | Feras | Completed | 2026-06-01 | 2026-06-05 | Implementation KPI Matrix (original plan) | Done
2 | WP1 Project Planning & Governance | Validate Project Scope | Scope approved by stakeholders ¦ Target: 100% Approved ¦ Verification: Scope Validation Report | LM Navigator Implementation Lead | Feras | Completed | 2026-06-07 | 2026-06-09 | Implementation KPI Matrix (original plan) | Done
3 | WP1 Project Planning & Governance | Define Technical Requirements | Technical specifications finalized ¦ Target: 100% Completed ¦ Verification: Technical Specification | Technical Solution Architect | Omar | Completed | 2026-06-11 | 2026-06-13 | Implementation KPI Matrix (original plan) | Done
4 | WP1 Project Planning & Governance | Conduct Coordination Meetings | Weekly coordination meetings ¦ Target: One meeting/week ¦ Verification: Minutes of Meetings | LM Navigator Implementation Lead | Feras | Ongoing | 2026-08-14 | 2026-10-31 | Implementation KPI Matrix (original plan)
5 | WP2 Human Resources & Mobilization | Recruit LM Navigator Implementation Lead | Position filled ¦ Target: 1 ¦ Verification: Signed Contract | GJU | Heba / Ziad | Completed | 2026-06-01 | 2026-06-05 | Implementation KPI Matrix (original plan) | Done
6 | WP2 Human Resources & Mobilization | Recruit Technical Solution Architect | Position filled ¦ Target: 1 ¦ Verification: Signed Contract | GJU | Heba / Ziad | Completed | 2026-06-07 | 2026-06-11 | Implementation KPI Matrix (original plan) | Done
7 | WP2 Human Resources & Mobilization | Recruit Content & Outreach Officer | Position filled ¦ Target: 1 ¦ Verification: Assignment Letter | GJU | Heba / Ziad | Completed | 2026-06-13 | 2026-06-17 | Implementation KPI Matrix (original plan) | Done
8 | WP2 Human Resources & Mobilization | Recruit Technical & QA Auditor | Position filled ¦ Target: 1 ¦ Verification: Contract | GJU | Heba / Ziad | In Progress | 2026-09-15 | 2026-09-22 | Implementation KPI Matrix (original plan)
9 | WP2 Human Resources & Mobilization | Assign Light M&E Officer | Position assigned ¦ Target: 1 ¦ Verification: Assignment Letter | GJU | Heba / Ziad | Completed | 2026-06-19 | 2026-06-19 | Implementation KPI Matrix (original plan) | Done
10 | WP2 Human Resources & Mobilization | Recruit Visa Content Developer | Position filled ¦ Target: 1 ¦ Verification: Contract |  | Heba / Ziad | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
11 | WP3 Branding & UX/UI | Develop Branding Identity | Branding package completed ¦ Target: Approved ¦ Verification: Branding Guidelines | Graphic Designer | Mohammad | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
12 | WP3 Branding & UX/UI | Develop Visual Theme | Theme approved ¦ Target: Approved Theme ¦ Verification: Design Approval | Graphic Designer | Mohammad | Completed | 2026-07-01 | 2026-07-05 | Implementation KPI Matrix (original plan) | Done
13 | WP3 Branding & UX/UI | Prepare UI Mockups | UI completed ¦ Target: 1 ¦ Verification: UI Mockups | Graphic Designer | Mohammad | Completed | 2026-07-07 | 2026-07-09 | Implementation KPI Matrix (original plan) | Done
14 | WP3 Branding & UX/UI | Prepare UX Prototype | UX completed ¦ Target: Approved Prototype ¦ Verification: UX Prototype | Graphic Designer | Mohammad | Completed | 2026-07-11 | 2026-07-13 | Implementation KPI Matrix (original plan) | Done
15 | WP4 Content Development | Develop Content Governance Methodology | Methodology approved ¦ Target: 1 Methodology ¦ Verification: Methodology Document | Content & Outreach Officer | Karma | Completed | 2026-07-01 | 2026-07-05 | Implementation KPI Matrix (original plan) | Done
16 | WP4 Content Development | Prepare Labour Mobility Content | Content completed ¦ Target: 1 ¦ Verification: Content Register | Content & Outreach Officer | Karma | In Progress | 2026-09-13 | 2026-09-15 | Implementation KPI Matrix (original plan)
17 | WP4 Content Development | Develop Visa Guidance | Visa content completed ¦ Target: 1 ¦ Verification: Validation Checklist | Content & Outreach Officer | Karma | In Progress | 2026-09-16 | 2026-09-20 | Implementation KPI Matrix (original plan)
18 | WP4 Content Development | Develop Labour Mobility Pathways | Pathways completed ¦ Target: All pathways available ¦ Verification: Review Report | Content & Outreach Officer | Karma | In Progress | 2026-09-21 | 2026-09-25 | Implementation KPI Matrix (original plan)
19 | WP4 Content Development | Prepare FAQ | Questions & Answers completed ¦ Target: Complete FAQ ¦ Verification: FAQ Register | Content & Outreach Officer | Karma | In Progress | 2026-09-26 | 2026-09-30 | Implementation KPI Matrix (original plan)
20 | WP4 Content Development | Develop AI Guidance Logic | AI decision logic completed ¦ Target: Rule-based logic operational ¦ Verification: AI Documentation | Content & Outreach Officer | Karma | In Progress | 2026-10-01 | 2026-10-05 | Implementation KPI Matrix (original plan)
21 | WP4 Content Development | Validate External Links | Verified links integrated ¦ Target: 100% valid ¦ Verification: Link Validation Report | Content & Outreach Officer | Karma | In Progress | 2026-10-09 | 2026-10-11 | Implementation KPI Matrix (original plan)
22 | WP5 Technical Development | Develop CMS Proof of Concept | CMS prototype completed ¦ Target: Operational ¦ Verification: PoC Report | Technical Solution Architect | Omar | Completed | 2026-07-01 | 2026-07-05 | Implementation KPI Matrix (original plan) | Done
23 | WP5 Technical Development | Prepare Test Environment | Test environment ready ¦ Target: Operational ¦ Verification: Environment Report | GJU IT | Omar | Completed | 2026-09-13 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
24 | WP5 Technical Development | Install CMS | CMS installed ¦ Target: Completed ¦ Verification: Installation Report | Technical Solution Architect | Omar | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
25 | WP5 Technical Development | Configure CMS | CMS configured ¦ Target: Completed ¦ Verification: Configuration Report | Technical Solution Architect | Omar | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
26 | WP5 Technical Development | Develop Website Structure | Website completed ¦ Target: 1 ¦ Verification: Development Report ¦ testing version | Technical Solution Architect | Omar | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
27 | WP5 Technical Development | Develop Navigation Structure | Navigation completed ¦ Target: Functional ¦ Verification: Functional Test | Technical Solution Architect | Omar | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
28 | WP5 Technical Development | Develop AI Supported Assistant | AI Assistant operational ¦ Target: Completed ¦ Verification: Technical Report | Technical Solution Architect | Omar | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
29 | WP5 Technical Development | Develop CMS Admin Panel | Admin interface operational ¦ Target: Completed ¦ Verification: Acceptance Report | Technical Solution Architect | Omar | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
30 | WP5 Technical Development | Optimize Website Performance | Performance optimized ¦ Target: Meets agreed benchmark ¦ Verification: Performance Test Report ¦ live version | Technical Solution Architect | Omar & QA | Not started | 2026-10-09 | 2026-10-15 | Implementation KPI Matrix (original plan)
31 | WP6 Infrastructure & Deployment | Prepare MODEE Cloud | Cloud ready ¦ Target: Operational ¦ Verification: Deployment Report | MODEE | Feras / MODEE | Not started | 2026-09-19 | 2026-09-21 | Implementation KPI Matrix (original plan)
32 | WP6 Infrastructure & Deployment | Prepare Production Environment | Production server configured ¦ Target: Ready ¦ Verification: Technical Report | MODEE | Feras / MODEE | Not started | 2026-09-22 | 2026-09-24 | Implementation KPI Matrix (original plan)
33 | WP6 Infrastructure & Deployment | Configure Domain | gjc.mol.gov.jo activated ¦ Target: Live ¦ Verification: DNS Verification | MODEE | Feras / MODEE | Not started | 2026-09-13 | 2026-10-01 | Implementation KPI Matrix (original plan)
34 | WP6 Infrastructure & Deployment | Configure Security Layers | Security completed ¦ Target: Firewall & SSL active ¦ Verification: Security Report | MODEE | Feras / MODEE | Not started | 2026-09-16 | 2026-10-01 | Implementation KPI Matrix (original plan)
35 | WP6 Infrastructure & Deployment | Deploy Production Platform | Platform launched ¦ Target: Go Live ¦ Verification: Go-Live Report | Technical Solution Architect | Omar & Anas | Not started | 2026-10-31 | 2026-11-04 | Implementation KPI Matrix (original plan)
36 | WP7 Testing & Quality Assurance | Functional Testing | Functional tests completed ¦ Target: Zero Critical Errors ¦ Verification: Functional Test Report | Technical & QA Auditor | QA | Not started | 2026-09-13 | 2026-09-19 | Implementation KPI Matrix (original plan)
37 | WP7 Testing & Quality Assurance | Integration Testing | Integration successful ¦ Target: Passed ¦ Verification: Integration Report | Technical & QA Auditor | QA | Not started | 2026-09-20 | 2026-09-26 | Implementation KPI Matrix (original plan)
38 | WP7 Testing & Quality Assurance | Cybersecurity Testing | Security assessment passed ¦ Target: Approved ¦ Verification: Cybersecurity Report | Technical & QA Auditor | QA | Not started | 2026-09-27 | 2026-10-03 | Implementation KPI Matrix (original plan)
39 | WP7 Testing & Quality Assurance | Resolve Bugs | Critical bugs closed ¦ Target: 100% resolved ¦ Verification: Bug Log | Technical Solution Architect | Omar & QA | Not started | 2026-10-15 | 2026-11-05 | Implementation KPI Matrix (original plan)
40 | WP7 Testing & Quality Assurance | User Acceptance Testing | UAT completed ¦ Target: Signed Acceptance ¦ Verification: UAT Report | MoL & GIZ | QA | Not started | 2026-10-04 | 2026-10-10 | Implementation KPI Matrix (original plan)
41 | WP7 Testing & Quality Assurance | Final QA Approval | QA completed ¦ Target: Approved ¦ Verification: QA Certificate | Technical & QA Auditor | QA | Not started | 2026-10-11 | 2026-10-13 | Implementation KPI Matrix (original plan)
42 | WP8 Launch & Handover | Train CMS Administrators | MoL staff trained ¦ Target: 1 ¦ Verification: Attendance Sheets | Technical Solution Architect | Omar/ Freas | In Progress | 2026-09-15 | 2026-10-15 | Implementation KPI Matrix (original plan)
43 | WP8 Launch & Handover | Deliver User Manual | Manual delivered ¦ Target: Completed ¦ Verification: User Manual | Technical Solution Architect | Rania & Karma & omar | Not started | 2026-09-15 | 2026-10-15 | Implementation KPI Matrix (original plan)
44 | WP8 Launch & Handover | Deliver Technical Documentation | Documentation delivered ¦ Target: Completed ¦ Verification: Technical Documentation¦ live version | Technical Solution Architect | Omar | Not started | 2026-11-16 | 2026-11-22 | Implementation KPI Matrix (original plan)
45 | WP8 Launch & Handover | Formal Handover | Handover completed ¦ Target: Signed ¦ Verification: Handover Certificate | GJU & MoL | Ziad | Not started | 2026-09-13 | 2026-10-15 | Implementation KPI Matrix (original plan)
46 | WP9 Sustainability & Monitoring | Prepare Warranty TOR | Prepare TOR Documents ¦ Target: Approved ¦ Verification: TOR | LM Navigator Implementation Lead & GJU | Feras | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
47 | WP9 Sustainability & Monitoring | Technical Evaluation of Warranty Offers/Proposals | Technical evaluation of received Warranty EOI/offers completed ¦ Target: Approved evaluation ¦ Verification: Technical Evaluation Report | LM Navigator Implementation Lead & GJU | Feras | In Progress | 2026-09-15 | 2026-09-20 | Added by M&E after 15 Sep 2026 team meeting
48 | WP9 Sustainability & Monitoring | Sign Warranty Agreement | Signing ¦ Target: Signed Agreement ¦ Verification: Signed Agreement | GJU & Contractor | Ziad | Not started | 2026-09-18 | 2026-09-24 | Implementation KPI Matrix (original plan)
49 | WP9 Sustainability & Monitoring | Activate Warranty | Warranty activated ¦ Target: 3-5 years ¦ Verification: Warranty Agreement | Contractor | Feras / Ziad | Not started | 2026-09-25 | 2026-09-27 | Implementation KPI Matrix (original plan)
50 | WP9 Sustainability & Monitoring | Establish Maintenance Plan | Maintenance procedures approved ¦ Target: Completed ¦ Verification: Maintenance Plan | Contractor | Feras / Ziad | Not started | 2026-09-28 | 2026-09-30 | Implementation KPI Matrix (original plan)
51 | WP9 Sustainability & Monitoring | Handover & Orientation | Handover to contractor ¦ Target: Completed ¦ Verification: Handover Documentation | Technical Solution Architect | Feras / Omar | Not started | 2026-10-15 | 2026-10-31 | Implementation KPI Matrix (original plan)
52 | WP9 Sustainability & Monitoring | Establish Content Governance | SOP approved ¦ Target: Completed ¦ Verification: Governance Manual | GJU | Karma / Rania / Ziad | Not started | 2026-09-13 | 2026-09-30 | Implementation KPI Matrix (original plan)
53 | WP9 Sustainability & Monitoring | Submit Progress Reports | Progress reports submitted ¦ Target: Monthly ¦ Verification: M&E Reports | Light M&E Officer | Waed | Completed | 2026-09-15 | 2026-09-15 | Implementation KPI Matrix (original plan) | Done
54 | WP9 Sustainability & Monitoring | Monitor KPIs | KPI dashboard updated ¦ Target: Monthly ¦ Verification: KPI Tracker | Light M&E Officer | Waed | Ongoing | 2026-08-14 | 2026-10-31 | Implementation KPI Matrix (original plan)
55 | WP9 Sustainability & Monitoring | Final Project Evaluation | Evaluation completed ¦ Target: Approved ¦ Verification: Final Evaluation Report | Light M&E Officer | Waed | Not started | 2026-10-15 | 2026-10-31 | Implementation KPI Matrix (original plan)
56 | WP1 Project Planning & Governance | Prepare & upload Minutes of Meeting (MoM) | After every internal Navigator meeting and every GIZ meeting |  | Heba | In Progress | 2026-08-14 | 2026-10-15 | Actual Tasks Tracker
57 | WP1 Project Planning & Governance | Regular weekly follow-up with the team | Weekly coordination meetings |  | Heba | In Progress | 2026-08-14 | 2026-10-31 | Actual Tasks Tracker
58 | WP1 Project Planning & Governance | Email to Alin - Navigator Follow-Up | Sent MoM, Governance & Methodology Report and materials to Alin for review/approval |  | Heba | Completed | 2026-07-20 | 2026-07-21 | Actual Tasks Tracker | Done
59 | WP1 Project Planning & Governance | Meeting with Waad | In-person briefing on the Navigator, EJIM project & M&E requirements |  | Heba | Completed | 2026-09-08 | 2026-09-08 | Actual Tasks Tracker | Done
60 | WP1 Project Planning & Governance | Initial meeting with Waed and Rania with the project team | Clarify key project matters with Dr. Ziad and Feras |  | Heba | Completed | 2026-09-09 | 2026-09-09 | Actual Tasks Tracker | Done
61 | WP1 Project Planning & Governance | Maintain team documentation on Google Drive | Ensure project documents are updated, organized and maintained |  | Heba | In Progress | 2026-08-14 | 2026-10-31 | Actual Tasks Tracker
62 | WP1 Project Planning & Governance | Create & organize project folders on Google Drive and share with team | Facilitate access, coordination and collaboration |  | Heba | In Progress | 2026-08-01 | 2026-10-31 | Actual Tasks Tracker
63 | WP1 Project Planning & Governance | Prepare the Navigator Team - Task & Progress Tracker | Tool to monitor responsibilities, tasks, status and progress |  | Waed | Completed | 2026-08-05 | 2026-08-07 | Actual Tasks Tracker | Done
64 | WP1 Project Planning & Governance | Follow up on Navigator team tasks & update the Tracker | Ongoing monitoring/updating of tasks and progress |  | Waed | In Progress | 2026-08-14 | 2026-10-31 | Actual Tasks Tracker
65 | WP1 Project Planning & Governance | Regular follow-up on GIZ-GJC coordination meetings | Track schedules, key discussions, action points & follow-up items |  | Heba | In Progress | 2026-08-14 | 2026-10-31 | Actual Tasks Tracker
66 | WP2 Human Resources & Mobilization | Align WP2 recruitment activities with the proposal | Reviewed and aligned recruitment activities with the project proposal |  | Heba | Completed | 2026-08-11 | 2026-08-12 | Actual Tasks Tracker | Done
67 | WP9 Sustainability & Monitoring | Prepare the M&E Indicator Tracking Matrix | Drafted and finalized the Implementation, KPI & Monitoring Matrix |  | Waed | Completed | 2026-07-23 | 2026-07-27 | Actual Tasks Tracker | Done
68 | WP9 Sustainability & Monitoring | Update the M&E Indicator Tracking Matrix | Revisions made directly in a meeting with Eng. Feras; finalized and approved by him |  | Heba | Completed | 2026-08-11 | 2026-08-11 | Actual Tasks Tracker | Done
69 | WP3 Branding & UX/UI | Follow up on posting the Warranty EOI on LinkedIn | EOI posting on LinkedIn completed |  | Heba | Completed | 2026-09-09 | 2026-09-09 | Actual Tasks Tracker | Done
70 | WP5 Technical Development | Follow-up email to Alin on the MASAR Navigator Warranty | Follow-up communication on the Warranty |  | Heba | Completed | 2026-08-16 | 2026-08-16 | Actual Tasks Tracker | Done
71 | WP5 Technical Development | Revise the Warranty TOR into an EOI format | Word & PDF versions prepared with required amendments |  | Heba | Completed | 2026-09-06 | 2026-09-07 | Actual Tasks Tracker | Done
72 | WP5 Technical Development | Prepare the EOI submission form for interested companies | Online EOI submission form prepared |  | Heba | Completed | 2026-09-06 | 2026-09-07 | Actual Tasks Tracker | Done
73 | WP5 Technical Development | Finalize and upload the EOI document | Final EOI document uploaded |  | Heba | Completed | 2026-09-07 | 2026-09-08 | Actual Tasks Tracker | Done
74 | WP5 Technical Development | Send EOI to potentially interested companies + build follow-up tracking list | Sent to contacts shared by Feras; tracking list created |  | Heba | Completed | 2026-09-08 | 2026-09-08 | Actual Tasks Tracker | Done
75 | WP1 Project Planning & Governance | Review GIZ documents, presentations, reports & flyers used previously for advisory sessions | Baseline review of existing GIZ material |  | Karma | Completed | 2026-07-07 | 2026-07-09 | Actual Tasks Tracker | Done
76 | WP1 Project Planning & Governance | Skim official German websites for beneficial information sources/links | Source discovery |  | Karma | Completed | 2026-07-10 | 2026-07-11 | Actual Tasks Tracker | Done
77 | WP4 Content Development | Follow one case on the pre-built track | Following one case start-to-end based on relevant options |  | Karma | Completed | 2026-07-15 | 2026-07-19 | Actual Tasks Tracker | Done
78 | WP4 Content Development | Build one full subject title for the chatbot question bank | One full subject prepared for the chatbot bank of questions |  | Karma | Completed | 2026-07-18 | 2026-07-19 | Actual Tasks Tracker | Done
79 | WP4 Content Development | Deliver outputs & GIZ validation | Delivered Governance report, one track, one case, one subject title to Dr. Ziad/Feras/GIZ |  | Karma | In Progress | 2026-07-19 | 2026-07-19 | Actual Tasks Tracker
80 | WP4 Content Development | Modify the 'Work and Vocational Training' track | Modified per GIZ comments |  | Karma | Completed | 2026-08-01 | 2026-08-08 | Actual Tasks Tracker | Done
81 | WP4 Content Development | Draft M&E Report Structure for the Navigator | Suggested structure covering all key M&E report titles |  | Karma | Completed | 2026-08-04 | 2026-08-08 | Actual Tasks Tracker | Done
82 | WP4 Content Development | Build the second semi-completed track (Study in Germany) | Second pathway drafted |  | Karma | Completed | 2026-08-09 | 2026-08-15 | Actual Tasks Tracker | Done
83 | WP4 Content Development | Build the third semi-completed track | Third pathway drafted |  | Karma | Completed | 2026-08-16 | 2026-08-20 | Actual Tasks Tracker | Done
84 | WP4 Content Development | Brief the content-upload person on concept, logic and display of content | Handover meeting with the CMS content uploader |  | Karma | Completed | 2026-08-21 | 2026-08-21 | Actual Tasks Tracker | Done
85 | WP4 Content Development | Present content logic/way-of-work at the official ToT workshop | Training/knowledge transfer session |  | Karma | Completed | 2026-08-26 | 2026-08-26 | Actual Tasks Tracker | Done
86 | WP4 Content Development | Send first two pathways for upload to MASAR website | Handover of validated content for publishing |  | Karma | Completed | 2026-08-27 | 2026-08-27 | Actual Tasks Tracker | Done
87 | WP1 Project Planning & Governance | Discuss solution requirements & scope with GIZ team | Requirements/scope alignment meeting |  | Feras | Completed | 2026-08-09 | 2026-08-11 | Actual Tasks Tracker | Done
88 | WP1 Project Planning & Governance | Meetings with GIZ, MoL, MODEE and internal Navigator team | Ongoing stakeholder coordination |  | Feras | In Progress | 2026-08-14 | 2026-10-31 | Actual Tasks Tracker
89 | WP1 Project Planning & Governance | Participate in M&E matrix preparation & review | Contributed to building/validating the KPI matrix |  | Feras | Completed | 2026-09-13 | 2026-09-13 | Actual Tasks Tracker | Done
90 | WP1 Project Planning & Governance | Follow up with team members on reaching project objectives | General progress follow-up |  | Feras | In Progress | 2026-09-14 | 2026-10-15 | Actual Tasks Tracker
91 | WP2 Human Resources & Mobilization | Participate in selecting needed resources (interviews & selection) | HR support |  | Feras | Completed | 2026-08-01 | 2026-08-03 | Actual Tasks Tracker | Done
92 | WP3 Branding & UX/UI | Participate in graphical design discussions and meetings | Design review input |  | Feras | Completed | 2026-08-01 | 2026-08-01 | Actual Tasks Tracker | Done
93 | WP4 Content Development | Participate in content preparation discussions & meetings | Content review input |  | Feras | Completed | 2026-08-01 | 2026-08-01 | Actual Tasks Tracker | Done
94 | WP4 Content Development | Participate in discussions on content publishing on the CMS | Publishing workflow input |  | Feras | Not started | 2026-10-01 | 2026-10-03 | Actual Tasks Tracker
95 | WP5 Technical Development | Research CMS-suitable technology platform & capabilities | Technology research |  | Feras | Completed | 2026-08-01 | 2026-08-05 | Actual Tasks Tracker | Done
96 | WP5 Technical Development | Decide solution design after CMS PoC | Design decision after PoC review |  | Feras | Completed | 2026-08-07 | 2026-08-07 | Actual Tasks Tracker | Done
97 | WP5 Technical Development | Participate in technical development discussions/review | Ongoing technical review input |  | Feras | In Progress | 2026-10-04 | 2026-10-08 | Actual Tasks Tracker
98 | WP5 Technical Development | Participate in test-environment preparation discussions | Test environment planning input |  | Feras | Completed | 2026-08-09 | 2026-08-11 | Actual Tasks Tracker | Done
99 | WP6 Infrastructure & Deployment | Participate in production-environment preparation discussions | Deployment planning input |  | Feras | Not started | 2026-10-09 | 2026-10-11 | Actual Tasks Tracker
100 | WP7 Testing & Quality Assurance | Participate in quality testing discussions | QA planning input |  | Feras | Not started | 2026-10-12 | 2026-10-18 | Actual Tasks Tracker
101 | WP8 Launch & Handover | Participate in ToT for MoL | Training of Trainers delivery support |  | Feras | Completed | 2026-08-01 | 2026-08-03 | Actual Tasks Tracker | Done
102 | WP8 Launch & Handover | Build & review the Warranty TOR | Warranty terms of reference drafted/reviewed |  | Feras | Completed | 2026-08-05 | 2026-08-09 | Actual Tasks Tracker | Done
103 | WP1 Project Planning & Governance | Meeting with GJC, MoL, MODEE | LM Navigator initiation meeting |  | Ziad | Completed | 2026-07-12 | 2026-07-12 | Actual Tasks Tracker | Done
104 | WP2 Human Resources & Mobilization | Hiring part-timers | Recruitment of part-time support staff |  | Ziad | In Progress | 2026-09-13 | 2026-10-05 | Actual Tasks Tracker
105 | WP2 Human Resources & Mobilization | Hiring QA technical auditor | Recruitment of Technical & QA Auditor |  | Ziad | In Progress | 2026-09-18 | 2026-09-22 | Actual Tasks Tracker
106 | WP3 Branding & UX/UI | Create Navigator concept demos | Three demo concepts produced |  | Ziad | Completed | 2026-07-04 | 2026-07-05 | Actual Tasks Tracker | Done
107 | WP3 Branding & UX/UI | Draft Navigator design & content guide | Word document guide |  | Ziad | Completed | 2026-06-14 | 2026-06-15 | Actual Tasks Tracker | Done
108 | WP3 Branding & UX/UI | Prepare MASAR concept for the Navigator | Concept document/images |  | Ziad | Completed | 2026-07-21 | 2026-07-22 | Actual Tasks Tracker | Done
109 | WP3 Branding & UX/UI | MASAR illustrated guide V1 | Illustrated platform guide |  | Ziad | Completed | 2026-07-21 | 2026-07-22 | Actual Tasks Tracker | Done
110 | WP5 Technical Development | Draft Warranty TOR | Initial Warranty Terms of Reference |  | Ziad | Completed | 2026-08-13 | 2026-08-15 | Actual Tasks Tracker | Done
111 | WP8 Launch & Handover | Capacity building for MoL on the LM Navigator (MASAR) | MoL orientation/training delivered |  | Ziad | Completed | 2026-08-11 | 2026-08-15 | Actual Tasks Tracker | Done
112 | WP3 Branding & UX/UI | Website wireframe v1 | Initial wireframe concept ideas |  | Mohammad | Completed | 2026-08-03 | 2026-08-07 | Actual Tasks Tracker | Done
113 | WP3 Branding & UX/UI | Website wireframe v2 | New wireframe based on comments from Navigator team & GIZ |  | Mohammad | Completed | 2026-07-10 | 2026-07-13 | Actual Tasks Tracker
114 | WP3 Branding & UX/UI | Website wireframe v3 | New wireframe based on comments from 14/7 meeting |  | Mohammad | Completed | 2026-07-15 | 2026-07-19 | Actual Tasks Tracker | Done
115 | WP3 Branding & UX/UI | Select naming and color palette | Set of names + vibrant colors selected per Alin's feedback |  | Mohammad | Completed | 2026-07-20 | 2026-07-21 | Actual Tasks Tracker | Done
116 | WP3 Branding & UX/UI | Website wireframe v4 | New static visuals using Eng. Karma's flow |  | Mohammad | Completed | 2026-07-22 | 2026-07-26 | Actual Tasks Tracker | Done
117 | WP3 Branding & UX/UI | Website wireframe v5 | New visuals based on new comments/feedback |  | Mohammad | Completed | 2026-07-26 | 2026-07-27 | Actual Tasks Tracker | Done
118 | WP3 Branding & UX/UI | Website wireframe v6 | New visuals based on new comments/feedback |  | Mohammad | Completed | 2026-07-27 | 2026-07-28 | Actual Tasks Tracker | Done
119 | WP3 Branding & UX/UI | Website wireframe v7 | New visuals based on new comments/feedback |  | Mohammad | Completed | 2026-07-28 | 2026-07-28 | Actual Tasks Tracker | Done
120 | WP3 Branding & UX/UI | Export wireframe v7 & share with Omar | Files shared in SVG/PDF/JSON formats |  | Mohammad | Completed | 2026-07-28 | 2026-07-30 | Actual Tasks Tracker | Done
121 | WP3 Branding & UX/UI | Create a new brand for the LMN (MASAR) | Brand identity built on selected names |  | Mohammad | Completed | 2026-08-06 | 2026-08-12 | Actual Tasks Tracker | Done
122 | WP3 Branding & UX/UI | Rework wireframe layout per GIZ comments | Logo placement, About Masar section, hero image options, GJC colors |  | Mohammad | Completed | 2026-08-02 | 2026-08-06 | Actual Tasks Tracker | Done
123 | WP3 Branding & UX/UI | Prepare MASAR final logo | Logo finalized for GIZ approval |  | Mohammad | In Progress | 2026-08-23 | 2026-08-24 | Actual Tasks Tracker
124 | WP3 Branding & UX/UI | Incorporate new logo & color palette into development | Assets handed to Omar for development |  | Mohammad | Completed | 2026-08-23 | 2026-08-24 | Actual Tasks Tracker | Done
125 | WP3 Branding & UX/UI | Landing page fine-tuning with Eng. Omar | Joint landing-page edits |  | Mohammad | Completed | 2026-09-07 | 2026-09-15 | Actual Tasks Tracker | Done
126 | WP1 Project Planning & Governance | Review proposal & define technical stack | Technology assessment document & recommended architecture for the website and CMS |  | Omar | Completed | 2026-07-01 | 2026-07-04 | Navigator Team Tracker (legacy - not yet re-confirmed in 2026 tracker) | Done
127 | WP5 Technical Development | Develop technology Proof of Concept | PoC discussed with Dr. Ziad & Eng. Feras |  | Omar | Completed | 2026-07-04 | 2026-07-05 | Navigator Team Tracker (legacy) | Done
128 | WP5 Technical Development | AI Assistant website prototype | Working prototype validating proposed technologies |  | Omar | Completed | 2026-07-05 | 2026-07-07 | Navigator Team Tracker (legacy) | Done
129 | WP5 Technical Development | Integrate Headless CMS into a simple website | Functional website integrated with an AI assistant |  | Omar | Completed | 2026-07-07 | 2026-07-11 | Navigator Team Tracker (legacy) | Done
130 | WP5 Technical Development | Headless CMS integration | Website with CMS and content management capability |  | Omar | Completed | 2026-07-11 | 2026-07-12 | Navigator Team Tracker (legacy) | Done
131 | WP5 Technical Development | Headless CMS + AI Assistant integration | Website with CMS + AI assistant decision tree |  | Omar | Completed | 2026-07-12 | 2026-07-13 | Navigator Team Tracker (legacy) | Done
132 | WP5 Technical Development | Unified platform development | Complete web platform combining all validated features |  | Omar | Completed | 2026-07-14 | 2026-07-18 | Navigator Team Tracker (legacy) | Done
133 | WP5 Technical Development | Final demonstration | End-to-end demo of feasibility/capability |  | Omar | Completed | 2026-07-19 | 2026-07-19 | Navigator Team Tracker (legacy) | Done
134 | WP3 Branding & UX/UI | Website with wireframe v7 | Build website on top of wireframe v7 |  | Omar | Completed | 2026-07-30 | 2026-09-15 | Navigator Team Tracker (legacy - design changed) | Done
135 | WP5 Technical Development | Payload CMS research & evaluation | Exploration, evaluation & production requirements |  | Omar | Completed | 2026-08-03 | 2026-08-08 | Navigator Team Tracker (legacy) | Done
136 | WP3 Branding & UX/UI | Landing page fine-tuning with Mohammad | Joint landing-page edits |  | Omar | Completed | 2026-09-07 | 2026-09-15 | Navigator Team Tracker (legacy) | Done
137 | WP4 Content Development | Coordinate with the Navigator team to receive verified content and prepare for upload | Awaiting CMS/website training before she can start uploading content herself |  | Rania | In Progress | 2026-09-16 | 2026-09-22 | Actual Tasks Tracker
138 | WP2 Human Resources & Mobilization | Support the hiring process (candidate shortlisting, etc.) | Planned task, no date/status recorded yet |  | Ziad / Heba / Feras | Completed | 2026-09-15 | 2026-09-15 | Navigator Team Tracker (legacy - planned, undated) | Done
139 | WP9 Sustainability & Monitoring | Submit, monitor and regularly update the M&E Plan | Planned task, no date/status recorded yet |  | Waed | In Progress | 2026-10-22 | 2026-10-24 | Navigator Team Tracker (legacy - planned, undated)
140 | WP1 Project Planning & Governance | Documentation and archiving | Planned task, no date/status recorded yet |  | Heba | In Progress | 2026-09-15 | 2026-10-31 | Navigator Team Tracker (legacy - planned, undated)
141 | WP8 Launch & Handover | Navigator component in the ToT for the Ministry of Labour | Planned task, no date/status recorded yet |  | Feras / Ziad / Karma | Completed | 2026-09-15 | 2026-09-15 | Navigator Team Tracker (legacy - planned, undated) | Done
142 | WP1 Project Planning & Governance | Draft MoU between GJU and MoL for post-31 Oct 2026 governance | Formalize GJU's continued content/advisory role after handover, subject to Secretary General approval |  | Ziad | Not started | 2026-10-15 | 2026-10-31 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
143 | WP1 Project Planning & Governance | Document the formal institutional governance charter (MoL / MODEE / GJU roles) | Written charter formalizing: MoL = domain/hosting/CMS ops/cloud allocation/costs; MODEE = cloud infra/cybersecurity/access control; GJU = platform dev/content/QA, no backend access |  | Ziad | Not started | 2026-10-15 | 2026-10-31 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
144 | WP2 Human Resources & Mobilization | Formalize dedicated GJU technical-oversight function for the full project lifecycle | Named owner(s) to supervise architecture/design decisions, enforce gateway-only & no-database principles, coordinate MODEE dependencies |  | Ziad | Completed | 2026-09-13 | 2026-09-15 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION | Done
145 | WP2 Human Resources & Mobilization | Assess procurement risk under the Unified Government Purchasing Bylaws for specialized technical roles | Risk note on how Main Purchasing Committee procedures may affect timeline/flexibility for QA Auditor & other specialized hires |  | Ziad | In Progress | 2026-09-28 | 2026-09-30 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
146 | WP5 Technical Development | Validate & stress-test the minimum system specification (2 CPU cores / 6GB RAM / 60GB storage, Linux) | Confirm sizing is sufficient for expected usage and concurrent load, in coordination with MODEE |  | QA | Not started | 2026-10-01 | 2026-10-15 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
147 | WP5 Technical Development | Finalize CMS product selection (Decap CMS / Strapi file-mode / Directus non-relational) | Selection must enforce flat-file, no-relational-database, git-based architecture and MODEE compliance |  | Omar / Feras | Completed | 2026-09-13 | 2026-09-13 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION | Done
148 | WP5 Technical Development | Set up the MODEE-approved Git-based CI/CD pipeline | Approved content/code changes trigger automated build & deployment |  | Omar | Completed | 2026-09-15 | 2026-09-15 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION | Done
149 | WP5 Technical Development | Enforce 'no personal data / no profiling / no autonomous decision-making' design principle during dev & code review | Architectural constraint check-off during developer procurement, technical design approval and code review |  | Feras / Omar | Completed | 2026-09-15 | 2026-09-15 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION | Done
150 | WP5 Technical Development | Document the rule-based decision-tree / chatbot knowledge base | Version-controlled, locked-down rule engine for the light AI-supported guidance module (no scoring/profiling) |  | Karma | Not started | 2026-09-13 | 2026-09-30 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
151 | WP6 Infrastructure & Deployment | Align VM, OS licensing/configuration with MODEE standards | System characteristics compliance check before deployment |  | MODEE / Omar | Completed | 2026-09-13 | 2026-10-09 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION | Done
152 | WP6 Infrastructure & Deployment | Implement Secure Government Network (SGN) access-control alignment | Network access restrictions aligned with SGN requirements, where applicable |  | Feras / MODEE | Not started | 2026-09-20 | 2026-10-10 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
153 | WP6 Infrastructure & Deployment | Set up MODEE-approved firewall and access-control protections | Applications protected by MODEE-approved firewall and security controls |  | Feras / MODEE | Not started | 2026-09-20 | 2026-10-10 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
154 | WP7 Testing & Quality Assurance | Verify the platform contains no relational database / no personal-data storage prior to sign-off | Compliance check against the core no-database design principle as part of final QA |  | Omar | Completed | 2026-09-15 | 2026-09-15 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION | Done
155 | WP9 Sustainability & Monitoring | Negotiate & sign the 3-5 year post-launch warranty & support agreement | Ensure system stability, security updates and continued CMS compatibility after handover |  | Ziad | In Progress | 2026-09-13 | 2026-10-01 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
156 | WP9 Sustainability & Monitoring | Establish post-launch technical-oversight function | Validate security, access-control arrangements and operational readiness before launch and during post-launch support |  | Ziad | Not started | 2026-10-15 | 2026-10-31 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
157 | WP9 Sustainability & Monitoring | Confirm long-term hosting/operation handover to MoL beyond the project duration | Document sustainability arrangement: Navigator is a long-term digital public service under MoL |  | Ziad | Not started | 2026-10-15 | 2026-10-31 | Proposed by M&E (derived from Project Proposal Document) - PENDING TEAM VALIDATION
158 | WP4 Content Development | Translate 'Work and Vocational Training' pathway content to Arabic | Translate the finalized Arabic Q&A content for this pathway into English | Content & Outreach Officer | Karma | Not started | 2026-09-15 | 2026-09-16 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
159 | WP4 Content Development | Translate 'Study in Germany' pathway content to Arabic | Translate the finalized Arabic Q&A content for this pathway into English | Content & Outreach Officer | Karma | Not started | 2026-09-16 | 2026-09-17 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
160 | WP4 Content Development | Translate 'Qualification Recognition' pathway content to Arabic | Translate the finalized Arabic Q&A content for this pathway into English | Content & Outreach Officer | Karma | Not started | 2026-09-17 | 2026-09-18 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
161 | WP4 Content Development | Translate 'Visa Preparation' pathway content to Arabic | Translate the finalized Arabic Q&A content for this pathway into English | Content & Outreach Officer | Karma | Not started | 2026-09-20 | 2026-09-22 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
162 | WP4 Content Development | Translate 'Language Improvement' pathway content to Arabic | Translate the finalized Arabic Q&A content for this pathway into English | Content & Outreach Officer | Karma | Not started | 2026-09-24 | 2026-09-26 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
163 | WP4 Content Development | Translate 'Job Market Readiness' pathway content to Arabic | Translate the finalized Arabic Q&A content for this pathway into English | Content & Outreach Officer | Karma | Not started | 2026-09-28 | 2026-09-29 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
164 | WP4 Content Development | Upload 'Work and Vocational Training' pathway content to the website (English) | Enter the English-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-15 | 2026-09-15 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
165 | WP4 Content Development | Upload 'Study in Germany' pathway content to the website (English) | Enter the English-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-16 | 2026-09-16 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
166 | WP4 Content Development | Upload 'Qualification Recognition' pathway content to the website (English) | Enter the English-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-17 | 2026-09-17 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
167 | WP4 Content Development | Upload 'Visa Preparation' pathway content to the website (English) | Enter the English-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-20 | 2026-09-20 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
168 | WP4 Content Development | Upload 'Language Improvement' pathway content to the website (English) | Enter the English-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-24 | 2026-09-24 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
169 | WP4 Content Development | Upload 'Job Market Readiness' pathway content to the website (English) | Enter the English-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-28 | 2026-09-28 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
170 | WP4 Content Development | Review 'Work and Vocational Training' pathway on the website after Rania's upload | QA check of the live pathway (Arabic + English) after Rania publishes it - content accuracy, links, display | Content & Outreach Officer | Karma | Not started | 2026-09-16 | 2026-09-16 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
171 | WP4 Content Development | Review 'Study in Germany' pathway on the website after Rania's upload | QA check of the live pathway (Arabic + English) after Rania publishes it - content accuracy, links, display | Content & Outreach Officer | Karma | Not started | 2026-09-17 | 2026-09-17 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
172 | WP4 Content Development | Review 'Qualification Recognition' pathway on the website after Rania's upload | QA check of the live pathway (Arabic + English) after Rania publishes it - content accuracy, links, display | Content & Outreach Officer | Karma | Not started | 2026-09-18 | 2026-09-18 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
173 | WP4 Content Development | Review 'Visa Preparation' pathway on the website after Rania's upload | QA check of the live pathway (Arabic + English) after Rania publishes it - content accuracy, links, display | Content & Outreach Officer | Karma | Not started | 2026-09-22 | 2026-09-22 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
174 | WP4 Content Development | Review 'Language Improvement' pathway on the website after Rania's upload | QA check of the live pathway (Arabic + English) after Rania publishes it - content accuracy, links, display | Content & Outreach Officer | Karma | Not started | 2026-09-26 | 2026-09-26 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
175 | WP4 Content Development | Review 'Job Market Readiness' pathway on the website after Rania's upload | QA check of the live pathway (Arabic + English) after Rania publishes it - content accuracy, links, display | Content & Outreach Officer | Karma | Not started | 2026-09-29 | 2026-09-29 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
176 | WP4 Content Development | Upload 'Work and Vocational Training' pathway content to the website (Arabic) | Enter the Arabic-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-16 | 2026-09-16 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
177 | WP4 Content Development | Upload 'Study in Germany' pathway content to the website (Arabic) | Enter the Arabic-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-17 | 2026-09-17 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
178 | WP4 Content Development | Upload 'Qualification Recognition' pathway content to the website (Arabic) | Enter the Arabic-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-18 | 2026-09-18 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
179 | WP4 Content Development | Upload 'Visa Preparation' pathway content to the website (Arabic) | Enter the Arabic-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-22 | 2026-09-22 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
180 | WP4 Content Development | Upload 'Language Improvement' pathway content to the website (Arabic) | Enter the Arabic-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-26 | 2026-09-26 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
181 | WP4 Content Development | Upload 'Job Market Readiness' pathway content to the website (Arabic) | Enter the Arabic-translated Q&A content into the CMS/website for this pathway | Visa Content Developer | Rania | Not started | 2026-09-29 | 2026-09-29 | Added directly by M&E after 13 Sep 2026 team review (Omar/Rania/Karma work split confirmed)
182 | WP4 Content Development | Prepare 'Work and Vocational Training' pathway content in English (finalize before upload) | English-language Q&A content finalized and ready for CMS entry ¦ Target: Content finalized ¦ Verification: Content file ready for Rania's upload | Content & Outreach Officer | Karma | Completed | 2026-09-10 | 2026-09-12 | Added by M&E (15 Sep 2026) - inserted to correct the Karma/Rania handoff sequence (English prep must precede English upload) | Done
183 | WP4 Content Development | Prepare 'Study in Germany' pathway content in English (finalize before upload) | English-language Q&A content finalized and ready for CMS entry ¦ Target: Content finalized ¦ Verification: Content file ready for Rania's upload | Content & Outreach Officer | Karma | Completed | 2026-09-10 | 2026-09-12 | Added by M&E (15 Sep 2026) - inserted to correct the Karma/Rania handoff sequence (English prep must precede English upload) | Done
184 | WP4 Content Development | Prepare 'Qualification Recognition' pathway content in English (finalize before upload) | English-language Q&A content finalized and ready for CMS entry ¦ Target: Content finalized ¦ Verification: Content file ready for Rania's upload | Content & Outreach Officer | Karma | Completed | 2026-09-14 | 2026-09-15 | Added by M&E (15 Sep 2026) - inserted to correct the Karma/Rania handoff sequence (English prep must precede English upload) | Done
185 | WP4 Content Development | Prepare 'Visa Preparation' pathway content in English (finalize before upload) | English-language Q&A content finalized and ready for CMS entry ¦ Target: Content finalized ¦ Verification: Content file ready for Rania's upload | Content & Outreach Officer | Karma | Not started | 2026-09-18 | 2026-09-20 | Added by M&E (15 Sep 2026) - inserted to correct the Karma/Rania handoff sequence (English prep must precede English upload)
186 | WP4 Content Development | Prepare 'Language Improvement' pathway content in English (finalize before upload) | English-language Q&A content finalized and ready for CMS entry ¦ Target: Content finalized ¦ Verification: Content file ready for Rania's upload | Content & Outreach Officer | Karma | Not started | 2026-09-22 | 2026-09-24 | Added by M&E (15 Sep 2026) - inserted to correct the Karma/Rania handoff sequence (English prep must precede English upload)
187 | WP4 Content Development | Prepare 'Job Market Readiness' pathway content in English (finalize before upload) | English-language Q&A content finalized and ready for CMS entry ¦ Target: Content finalized ¦ Verification: Content file ready for Rania's upload | Content & Outreach Officer | Karma | Not started | 2026-09-26 | 2026-09-28 | Added by M&E (15 Sep 2026) - inserted to correct the Karma/Rania handoff sequence (English prep must precede English upload)